## Sayfa1
Week |  | 1 | 2 | 3 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
CENG407 Deadlines | Progress Status | 11 October 2024 | 18 October 2024 | 25 October 2024 | 1 November 2024 | 8 November 2024 | 15 November 2024 | 22 November 2024 | 29 November 2024 | 6 December 2024 | 13 December 2024 | 20 December 2024 | 27 December 2024 | 3 January 2025 | 10 January 2025 | ?? January 2024
Team Setup | Completed | bar: 1
Project Proposal Form | Completed | bar: 1
Project Selection Form | Completed | bar: 2
GitHub Repository | Completed | bar: 2
Project Work Plan | Completed | bar: 3
Literature Review | In Progress | bar: 2 to 6
Software Requirements Specification | Pending | bar: 5 to 10
Project Webpage | Pending | bar: 10 to 11
Software Design Description | Pending | bar: 12 to 13
Project Report / Project Tracking Form | Pending | bar: 14 to 15
Presentation | Pending | bar: 16